## organizations
id | name | type | industry | notes
ORG-001 | AeroSight Robotics | internal | Robotics / Autonomous Systems
ORG-002 | Northstar Energy | customer | Energy / Utilities
ORG-003 | VectorNav Components | vendor | Navigation / IMU Hardware

## contacts
id | organization_id | name | role | email
CON-001 | ORG-002 | Sarah Chen | Director of Operations | sarah.chen@northstar-energy.com
CON-002 | ORG-003 | Marcus Webb | Account Manager | marcus.webb@vectornav.com

## employees
id | name | role | email | department
EMP-001 | Alex Morgan | Project Manager | alex.morgan@aerosight.io | Program Management
EMP-002 | Jordan Lee | Mechanical Engineer | jordan.lee@aerosight.io | Hardware
EMP-003 | Sam Rivera | Engineering Lead | sam.rivera@aerosight.io | Software
EMP-004 | Taylor Kim | Software Engineer | taylor.kim@aerosight.io | Software

## projects
id | name | status | target_date | pm_id | customer_org_id | description
PROJ-001 | Northstar Autonomous Inspection Pilot | at_risk | 2025-10-15 | EMP-001 | ORG-002 | Autonomous inspection-drone system for Northstar Energy facility corridors.

## meetings
id | project_id | title | date | attendees | notes | processed
MTG-001 | PROJ-001 | Weekly Status — AeroSight / Northstar | 2025-08-20 | EMP-001;EMP-003;CON-001 | Reviewed software milestones. Navigation prototype on track. | yes
MTG-002 | PROJ-001 | Northstar Design Review | 2025-08-28 | EMP-001;EMP-002;EMP-003;CON-001 | Customer design review with Northstar Energy. Northstar requires the drone to fit through a 620mm clearance in Corridor C access hatches. Current AeroSight enclosure width is 640mm — redesign required before pilot deployment. Navigation field testing depends on VectorNav firmware delivery for corridor routing. Northstar confirmed the final pilot date of October 15 cannot move. Northstar requires a live demonstration before their September 25 safety review board. | no
MTG-003 | PROJ-001 | VectorNav Vendor Check-in | 2025-09-03 | EMP-003;CON-002 | VectorNav firmware v2.4.1 was expected September 6. New delivery date communicated: September 12 due to calibration pipeline delay. This impacts navigation integration testing and demo video timeline. | no

## requirements
id | project_id | title | description | source_meeting_id | status
REQ-001 | PROJ-001 | Autonomous corridor navigation | Drone must navigate Corridor C autonomously with sub-meter accuracy. |  | approved
REQ-002 | PROJ-001 | Thermal imaging inspection | Capture thermal anomalies along inspection path for safety reporting. |  | approved

## risks
id | project_id | title | description | severity | status | source
RISK-001 | PROJ-001 | Schedule compression before safety review | Hardware redesign and firmware dependency reduce available testing time before client safety review. | high | open | MTG-002

## dependencies
id | project_id | title | description | owner_id | external_org_id | expected_date | status
DEP-001 | PROJ-001 | VectorNav firmware v2.4.1 | Firmware required for corridor navigation integration tests. | EMP-003 | ORG-003 | 2025-09-06 | pending

## work_items
id | type | title | description | project_id | owner_id | status | priority | due_date | dependencies | source | related_meeting_id | related_github | acceptance_criteria | code_status | ci_status | physical_validation
TASK-101 | task | Enclosure mechanical design | Current enclosure 640mm wide; target 620mm max width. | PROJ-001 | EMP-002 | in_progress | high | 2025-09-18 |  | Initial project plan |  |  |  | not_started |  | not_started
TASK-104 | feature | Corridor C Navigation | Autonomous routing through Corridor C with obstacle avoidance. | PROJ-001 | EMP-004 | in_progress | high | 2025-09-20 | DEP-001 | REQ-001 |  | PR #148 | 18/18 simulation tests pass; field validation after firmware delivery | complete | passed | blocked
TASK-105 | task | Thermal camera validation | Validate thermal imaging pipeline for safety reporting. | PROJ-001 | EMP-004 | todo | medium | 2025-09-22 |  | REQ-002 |  |  |  | in_progress |  | not_started
MS-001 | milestone | Northstar Safety Review Demo | Live demonstration before Northstar safety review board. | PROJ-001 | EMP-001 | blocked | critical | 2025-09-25 | DEP-001;TASK-101;TASK-104 | Customer contract

## project_assignments
employee_id | project_id | role
EMP-001 | PROJ-001 | Project Manager
EMP-002 | PROJ-001 | Mechanical Engineer
EMP-003 | PROJ-001 | Engineering Lead
EMP-004 | PROJ-001 | Software Engineer

## stakeholder_relationships
project_id | contact_id | relationship
PROJ-001 | CON-001 | customer_sponsor
PROJ-001 | CON-002 | vendor_account

## actions
id | project_id | meeting_id | description | owner_id | due_date | status
ACT-001 | PROJ-001 | MTG-002 | Mechanical team to assess 620mm redesign options | EMP-002 | 2025-09-05 | open

## development_requests
id | project_id | title | linked_work_item | github_repo
DEV-001 | PROJ-001 | Corridor C navigation module | TASK-104 | aerosight/northstar-inspection-drone

## milestones
id | project_id | title | due_date | status
MS-001 | PROJ-001 | Northstar Safety Review Demo | 2025-09-25 | blocked